## Project Plan
Task ID | Task Name | Duration | Start Date | End Date | Predecessors | Resource Names
1 | Planning and Approval | 10 days | 2024-12-11 | 2024-12-24 | - | IT Director
2 | Site Survey | 5 days | 2024-12-15 | 2024-12-19 | 1 | Technical Specialist
3 | Procurement | 10 days | 2024-12-25 | 2025-01-07 | 1 | Project Manager
4 | Cybersecurity Setup | 7 days | 2025-01-02 | 2025-01-09 | 3 | IT Security Analyst
5 | Installation | 10 days | 2025-01-08 | 2025-01-21 | 3,4 | Technical Specialist
6 | Testing and Calibration | 5 days | 2025-01-15 | 2025-01-19 | 5 | Technical Specialist
7 | Training | 5 days | 2025-01-22 | 2025-01-28 | 5 | Community Coordinator
8 | Launch and Monitoring | 5 days | 2025-01-29 | 2025-02-05 | 6,7 | IT Director

## Risk Assessment
Risk | Description | Risk Level | Impact | Mitigation Strategy
Privacy Concerns | Students, staff, or parents may feel uncomfortable with surveillance cameras. | High | High | Conduct stakeholder meetings to explain the purpose and security benefits of the cameras.
Cybersecurity Threats | Risk of unauthorized access to the camera feeds, potentially exposing sensitive information. | High | High | Encryption of the stream and a network, and the examination of security at least once a year.
Budget Constraints | Project may exceed allocated funds for procurement, installation, or maintenance. | Medium | High | Get competitive bids, seek and obtain supplemental funds, and provide for a few backstops.
Technical Failures | Cameras or software may malfunction, especially during critical moments. | Medium | Medium | Schedule regular maintenance and testing; procure backup equipment.
Environmental Factors | Outdoor cameras may face damage due to weather conditions (e.g., rain, snow, high temperatures). | Medium | Medium | Use weather-resistant equipment and ensure installation is performed to withstand local environmental conditions.
Legal Compliance | Possible problems in surveillance laws or privacy laws. | High | High | Consult legal counsel to ensure compliance with local laws and regulations.
Stakeholder Resistance | Some school administrators, teachers or even police may not support the project | Medium | Medium | Organization of meetings to discuss the project with respect to the aims and objectives of the school and security.
Installation Delays | Delays in procurement, installation, or training could impact project timelines. | Medium | Medium | Set realistic deadlines are to be set, a time line for work needs to be prepared and kept reviewable constantly.

## Funding Sources
Funding Source | Description
School Budget | Spend a portion of the school’s annual operating expenses to finance the installation of security cameras.
Government Grants | Open state or Federal Grant Programs for school improvement and specifically school safety and security.
Community Donations | Reach out to local businesses, alumni, and parent-teacher organizations (PTA) for sponsorship and support.
Fundraising Events | Arrange charity sales including bake sale, raffle selling, or even car wash to get more money.
Private Partnerships | Partner with technology companies or local security firms to sponsor or donate equipment or services.

## APA Citations
Source | Title | Retrieved From
Microsoft Corporation | Getting started with Microsoft Project | https://www.microsoft.com
Khan Academy | Introduction to project management tools [Video] | https://www.khanacademy.org